## Slide 1: Status & Goal
LOI approved on Oct. 02
  “proceeding as rapidly as possible to a full implementation, ideally in time for Run-4”
Next Step; Conceptual Design Report
  Fix design, makeup mechanical drawings etc
  Homeworks (simulations);
    Detailed PID scheme (M. Shimomura)
    Rate estimates and triggers (K.Ozawa/S.Sato)
    Effects on EMCal (S. Takagi with ??)
    Which sector on the West Arm
  Plan to submit CDR by Feb 03
Aim to install the aerogel before RUN-4
  Run-4 will be the major Au-Au run at full energy

## Slide 2: Design
Base of Design
  Enough segmentations
    Occupancy <10%
  Enough # of photoelectron
    At least 10 - 15 p.e.
  Flat response
  No dead space in between
  Aerogel at the same radial location
Backgrounds;
  Chrenkov emission at pmt window
  Scintillation Emission?
  Delta-ray?
Effects on detectors behind us;
  EM-Cal
  Pad Chamber

## Slide 3: Config. with Belle-type

## Slide 4: Config. with Integration-type

## Slide 5: Other Configurations
Zolin II type
  11 x 17
  Easier preparation of aerogel
  Complicated structure
Zolin III type
  22 x 11
  No cut of aerogel required
  Easier structure
Should make decision on the configuration from this test run.
  # of p.e.
  Flatness
  Timing property

## Slide 6: Selection & Purchase of PMT
3” PMT; R6233-01HA
  Gain ; > 2.7 x 10**5 with 2-2-1-… bleeder at 1kV
  Q.E. ; 30 % (typ.)
P.O. of 320 PMT’s submitted
  @37800yen(~$315)
  To be delivered by March 03.

## Slide 7: Selection & Purchase of Aerogel
Hydrophobic is a “must”.
  Matsushita
  Index of 1.007, 1.015 & 1.020
Index is key parameter
Still under negotiation with Matsushita for conditions
  Index will be ~ 1.012
  >400 liter will be delivered before August 03.
  Final cost may be significantly higher than $400/liter

## Slide 8: Location on the West Arm
Enough radial space for Aerogel + TOF?
19 inches of free space
  43 cm ? - 48.26 cm

## Slide 9: Which Sector on the West?
Two possible location;
  Green or blue
How it looks like when installed on East
TOF 1 panel ; 0.5 m x 2 m
Aerogel
2 m x 2 m
(~180 segments)

## Slide 10: Which sector to be installed?
Vertical sector;
  Mechanically Stable
  Symmetric& Full acceptance for + & - charges
  Maybe difficult to install
Needs to be settled at BNL with team of P.Kroon.

## Slide 11: Photo of West arm
“upper limit on the depth of a new detector - 330mm is probably entirely due to the space in the towers available for insertion of the detector (if done through the tower)”
“1.5m(Z) x 4.33*0.15(theta) = 1.5 x 1.5 m2”

## Slide 12: Goal of this meeting
Make decision on the configuration!
Make plan towards mass production!
Make up “To do lists” for CDR with names!
Have fun at party!

## Slide 13: Results of 15 x 15 cell
Aerogel/Integ ; 12/12 cm
  Normal ; 17 p.e. at center, 15 p.e. corner
  Backward; 14 p.e.~ 14 p.e.
Aerogel.Integ; 12/ 9 cm
  Normal; 18 p.e.(center) - 18 (3,3)
  Backward; 16 p.e. ~ 14 p.e.(6,6)
Aerogel/Integ ; 9/10 cm (Small Box)
  Normal; 13 p.e. ~ 12 p.e.
  Backward ; --
Aerogel/Integ; 9/9 cm
  Normal ; 15 p.e. ~ 14 p.e. (x,y)=(6,6)
  Backward ; --
Aerogel/Integ; 6/9 cm
  Normal ; 13 p.e. ~ 11 p.e.
  Backward ; 11 p.e. ~ 10 p.e. (corner)

## Slide 14: Zolin II
11.5 (Hor) x 17 (Ver) cm
Aerogel/Integ ; 11/11 cm
Normal ; 18 p.e. @center ~ 18 p.e.
Bacward ; 15 p.e. @center ~ 15 p.e.@(4,4.5)

## Slide 15: Zolin III
Aerogel/Integ ; 12/9 cm
22 (Hor) x 11 (ver) cm
Aerogel/Integ ;
Normal ; 16 p.e.(Center) ~ 17 p.e.(Edge)~ 13 p.e.(Corner)
Backward; 10 p.e. (center) ~ 10 p.e.(Corner)

## Slide 16: Issues Raised
FEE 90 ohm impedance instead of 50 ohm
Gain of pre-Amp?
Do we need pre-amp really?
Timing Threshold at ~1p.e.!
LED pulser
Aluminum Thickness ; 0.2 - 0.5 mm
Structural analysis Needed!

## Slide 17: Plan
Choose Configuration
  1st; Zolin II type
  2nd; 15 x 15 Cell
  Confirm the results tomorrow
  Decision before X’mass
Mechanical design
  Structural analysis
    Strength/Tolerance
  S. Afanasiev at Dubna
  First Drawings by Jan 03
Discussion/Feedback from P. Kroon team in Jan 03.
FEE
  Pre-amp?
  Bleeder
    Prototype Test In Jan 03
Simulations
  Detailed PID scheme (M. Shimomura)
  Rate estimates and triggers (K.Ozawa/S.Sato)
  Effects on EMCal (S. Takagi with ??)
  Which sector on the West Arm
Submit CDR by the end of Feb 03 !

## Slide 18: Mass Production
PMT
  Calibration (Tsukuba)
  Bleeder (Tsukuba)
  Starting in March 03
Aerogel
  Quality Control (Tsukuba)
  Partial delivery in spring
  Total by Aug 03
GORETEX Reflector
  Innerbox (Tsukuba)
FEE
  Tokyo CNS
Mechanical Structure
  Box Construction (Dubna)
  Aerogel cut ? (Dubna? KEK?)
  Big structure (BNL)
Analysis
  PISA routine